## Sheet1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Link git: https://github.com/Hekio-Kun/SoundWaveProject.git
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Deadline | Time: Resit | Note
Login | User Authentication | Simple | Iteration 1 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-10-10 | 2026-11-10 | Done
Register Account | User Authentication | Medium | Iteration 1 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Verify Email | User Authentication | Medium | Iteration 1 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Forgot and Reset Password | User Authentication | Medium | Iteration 1 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
View Profile | Profile Management | Medium | Iteration 3 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Update Profile | Profile Management | Medium | Iteration 3 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Logout | User Authentication | Simple | Iteration 2 | CE190466 | DuyLH | Iteration 1 | 2026-09-10 | 2026-10-10 | 2026-11-10 | Done
Create Custom Lyric | Lyrics Interaction | Simple | Iteration 2 | CE190466 | DuyLH | Iteration 2 | 14/10/2026 | 20/10/2026 | 23/10/2026 | Done
View Synchronous Lyric Public | Lyrics Interaction | Meidum | Iteration 2 | CE190466 | DuyLH | Iteration 2 | 14/10/2026 | 20/10/2026 | 23/10/2026 | Done
Update Synchronous Lyric Public | Lyrics Interaction | Complex | Iteration 2 | CE190466 | DuyLH | Iteration 3
View Custom Lyric | Lyrics Interaction | Simple | Iteration 3 | CE190466 | DuyLH | Iteration 3
Update Custom Lyric | Lyrics Interaction | Medium | Iteration 3 | CE190466 | DuyLH | Iteration 3
Delete Custom Lyric | Lyrics Interaction | Simple | Iteration 3 | CE190466 | DuyLH | Iteration 3
View Ranking Board | Music Search & Browsing | Medium | Iteration 1 | CE200338 | HaoTNT | Iteration 2 | 15/10/2026 | 17/10/2026 | 18/10/2026 | Done
Stream Music | Audio Playback | Complex | Iteration 2 | CE200338 | HaoTNT | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
Control Playback | Audio Playback | Medium | Iteration 1 | CE200338 | HaoTNT | Iteration 1 | 2026-10-10 | 2026-12-10 | 13/10/2026 | Done
View Listening History | Music Interaction | Medium | Iteration 2 | CE200338 | HaoTNT | Iteration 2 | 14/10/2026 | 16/10/2026 | 17/10/2026 | Done
Add Track to Favorites | Music Interaction | Simple | Iteration 2 | CE200338 | HaoTNT | Iteration 2 | 15/10/2026 | 18/10/2026 | 23/10/2026 | Done
View Favorite Tracks | Music Interaction | Simple | Iteration 2 | CE200338 | HaoTNT | Iteration 2 | 15/10/2026 | 18/10/2026 | 23/10/2026 | Done
Remove Song from Favorites | Music Interaction | Simple | Iteration 2 | CE200338 | HaoTNT | Iteration 2 | 15/10/2026 | 18/10/2026 | 23/10/2026 | Done
View Staff Directory | System Administration | Medium | Iteration 2 | CE200338 | HaoTNT | Iteration 3
Create Staff Account | System Administration | Medium | Iteration 2 | CE200338 | HaoTNT | Iteration 3
Deactivate Staff Account | System Administration | Simple | Iteration 3 | CE200338 | HaoTNT | Iteration 3
View Staff Moderation Activity | System Administration | Medium | Iteration 3 | CE200338 | HaoTNT | Iteration 3
Send Account Credentials Email | System Administration | Simple | Iteration 3 | CE200338 | HaoTNT | Iteration 3
Filter Public Catalog | Music Search & Browsing | Simple | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 2026-10-10 | 2026-11-10 | Done
View My Notification | Notification Management | Simple | Iteration 2 | CE201233 | TuanTA | Iteration 2 | 15/10/2026 | 16/10/2026 | 17/10/2026 | Done
Create A Playlist | Playlist Management | Medium | Iteration 2 | CE201233 | TuanTA | Iteration 2 | 2026-10-10 | 13/10/2026 | 14/10/2026 | Done
View My Playlists | Playlist Management | Medium | Iteration 2 | CE201233 | TuanTA | Iteration 2 | 2026-10-10 | 13/10/2026 | 14/10/2026 | Done
Update My Playlist | Playlist Management | Medium | Iteration 2 | CE201233 | TuanTA | Iteration 2 | 2026-10-10 | 13/10/2026 | 14/10/2026 | Done
Delete A Playlist | Playlist Management | Medium | Iteration 2 | CE201233 | TuanTA | Iteration 2 | 2026-10-10 | 13/10/2026 | 14/10/2026 | Done
Submit Track For Review | Track Management | Simple | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 22/10/2026 | 24/10/2026 | 25/10/2026 | Done
Create Track Draft | Track Management | Complex | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
View Tracks List | Track Management | Simple | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
Update Track | Track Management | Complex | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
Delete Track | Track Management | Medium | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
View Track Details | Track Management | Complex | Iteration 1 | CE201233 | TuanTA | Iteration 1 | 2026-09-10 | 13/10/2026 | 14/10/2026 | Done
Search Public Catalog | Music Search & Browsing | Medium | Iteration 1 | CE201233 | TuanTA | Iteration 3
View Recommended Song | Music Search & Browsing | Medium | Iteration 3 | CE201183 | PhucDTT | Iteration 3
View Rejection Reason | Track Management | Medium | Iteration 1 | CE201183 | PhucDTT | Iteration 1 | 2026-09-10 | 2026-10-10 | 2026-11-10 | Done
View Album Details | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 22/10/2026 | 24/10/2026 | 25/10/2026 | Done
Submit Album For Review | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 22/10/2026 | 24/10/2026 | 25/10/2026 | Done
Create An Album | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
View Albums List | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
View System Statistics | System Administration | Complex | Iteration 3 | CE201183 | PhucDTT | Iteration 3
Update Albums | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Delete Albums | Album Management | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 2 | 2026-09-10 | 2026-11-10 | 2026-12-10 | Done
Create A Content Report | Content Reporting | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 3
View Content Report | Content Reporting | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 3
Update Content Report | Content Reporting | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 3
Withdraw Content Report | Content Reporting | Medium | Iteration 2 | CE201183 | PhucDTT | Iteration 3
View Track Moderation List | Content Moderation | Medium | Iteration 1 | CE190726 | TriNM | Iteration 2 | 14/10/2026 | 19/10/2026 | 20/10/2026 | Done
Update Track Moderation | Content Moderation | Medium | Iteration 1 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 14/10/2026 | 15/10/2026 | Done
Search Moderation Track | Content Moderation | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 14/10/2026 | 15/10/2026 | Done
Filter Moderation Track | Content Moderation | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 14/10/2026 | 15/10/2026 | Done
View Track Moderation Detail | Content Moderation | Simple | Iteration 3 | CE190726 | TriNM | Iteration 2 | 14/10/2026 | 19/10/2026 | 20/10/2026 | Done
View User Reports | Content Moderation | Simple | Iteration 2 | CE190726 | TriNM | Iteration 3
Resolve Content Report | Content Moderation | Medium | Iteration 2 | CE190726 | TriNM | Iteration 3
Take Down Published Track | Content Moderation | Complex | Iteration 2 | CE190726 | TriNM | Iteration 3
Create A Genre | System Administration | Simple | Iteration 2 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done
View Genres | System Administration | Simple | Iteration 2 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done
Update A Genre | System Administration | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done
Deactivate Genre | System Administration | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done
Search Genre | System Administration | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done
Filter Genre | System Administration | Simple | Iteration 3 | CE190726 | TriNM | Iteration 1 | 2026-10-10 | 16/10/2026 | 17/10/2026 | Done